## Product Backlog
ID | Story Title | User Story | Acceptance Criteria | Business Value | Estimation | Status
1 | Development / Create an environment | As a Developer, I want to have a version-controlled Java project, where a Java webserver serves requests So that I can start developing in a sandboxed environment | Given I startup my Java web-application server When I open http://localhost:8080 in my browser Then ensure the server gives back an index page | 100 |  | Done
2 | Products / List | As a User, I want to have an index page, where I can see the list of Products within a default Product Category So that I can browse Products within that Category. | Given I have Products and a default Product Category in the application When I open the root url (/) Then ensure I can see a list of Products And ensure that the following details are displayed: - product title - description - image - price | 100 |  | Done
3 | Products / by Product Category | As a User, I want to have an index page, where I can filter Products by Product Categories So that I can browse Products within any Category | Given I have Products and Product Categories listed on the index page When I I click on a Category's title Then ensure it displays the Products only in the selected Category | 200 |  | Done
4 | Products / by Supplier | As a User, I want to have an index page, where I can filter Products by Suppliers So that I can browse Products by Suppliers too | Given I have Products and Suppliers listed on the index page When I I click on a Supplier's name Then ensure it displays the Products only for the selected Supplier | 200 |  | Done
5 | Shopping Cart / add to Cart | As a User, I want to have a Shopping Cart So that I can add products which I want to buy. | Given I have a Product list And the Products have an "Add to cart" button When I click on the "Add to cart" button Then ensure it creates a new Order for storing cart data of the User And ensure it creates a new LineItem with the quanity (default: 1) and price (the price of the Product) And ensure it stores this data on the server. And ensure it displays the number of cart items in the Page header. | 500
6 | Shopping Cart / Review | As a User, I want to review my Shopping Cart So that I can review the items in my shopping cart before checking out so that I can see what I've already selected. | Given I have a Shopping Cart with items in it When I click on the "Shopping cart" menu item in the Page header Then ensure it displays the items (LineItems) with the following data: - name of the Product - quantity - unit price / subtotal price And ensure it displays the total price of all the items in the cart | 300
7 | Shopping Cart / Edit | As a User, I want to edit the items in my Shopping Cart So that I can modify the items when i change my mind - by changing quantity or removing items. | Given I have a Shopping Cart review page And the LineItems are displayed in a form And the quantities are displayed in input fields When I change the quantity of an item Then ensure it stores the new quantity of the LineItem When I change the quantity to 0 Then ensure it removes the LineItem from the cart | 400
8 | Shopping Cart / Checkout | As a User, I want to checkout the items from the Shopping Cart So that I can order the Products. | Given I have a Shopping Cart review page When I click on the "Checkout" button Then ensure it asks the following data from the User: - Name - Email - Phone number - Billing Address (Country, City, Zipcode, Address) - Shipping Address (Country, City, Zipcode, Address) And it stores the validated data to the Order Then it redirects to the Payment page | 500
9 | Shopping Cart / Payment | As a User, I want to pay for my Products So that I can complete the payment online. | Given I checked-out the items from the Shopping cart Then I can see the total price what I have to pay And I can choose from the following payment methods: - credit card - paypal Then based on the selected payment method I can enter the credentials for the payment provider: - credit card: card number, card holder, expiry date, code - paypal: username and password | 700
10 | Shopping Cart / Confirmation | As a User, I want to see the result of my payment So that I can get a confirmation about my Order. | Given I made a payment Then I can see the result of the transaction: - In case of error: the details of the error - In case of success: the Confirmation page with the details of the Order Then ensure it saves the Order into a JSON file Then ensure it sends an email to the User about the Order | 600
11 | Admin log | As an Admin, I want to have a logfile about the checkout processes (per Order) So that I can see the steps of every Order and investigate issues. | Given the User started a checkout process Then ensure it saves all the steps and details into a JSON file (where the filename is the Order ID and Date) | 300

## Sprint 1 Backlog
Story ID | Task ID | Task Description | Estimation | Responsible | Status |  | Monday | Tuesday | Wednesday | Thursday | Friday | Demo
[6 empty] | Remaining | 0 | 0 | 0 | 0 | 0 | 0